CadetX Virtual Work Experience

Heavy Supplier, Inventory & Warehouse Analytics

Sprint 01 Plan - Draft for Team Discussion and Approval

Sprint 1: Friday 23 October - Thursday 29 October 2026

| Item | Detail |
| --- | --- |
| Document status | DRAFT v0.1 - prepared by Thomars (Scrum Master, Week 1) for review and approval by all members at the Sprint 1 planning meeting |
| Meeting | Friday 23 October 2026 - Sprint 1 planning meeting (60 minutes, online) |
| Prepared for | Keren Oyem (Data Analyst) and David (Data Analyst) |
| How to use | Read before the meeting. Every item marked 'proposed' can be changed. Decisions are recorded in Section 2 and the plan becomes v1.0 once all three members approve it in Section 13. |

# 1. Sprint Overview

| Item | Detail |
| --- | --- |
| Sprint | Sprint 1 of 12 - Phase 1: Foundation & Exploration |
| Official start | Friday 23 October 2026 (Day 1 of 91) |
| Sprint window | Friday 23 October 2026 to Thursday 29 October 2026 (7 days), with preparation on Thursday 22 October |
| Scrum Master | Thomars (also Data Scientist) - Week 1 of the rotation |
| Team | Thomars - Scrum Master and Data Scientist; Keren Oyem - Data Analyst; David - Data Analyst |
| Catalogue task | A1 Data Profiling & Structure Analysis, plus the brief's required KPI proposal and analysis questions |
| Team capacity (proposed) | 60 hours (3 members x about 20 hours) - each member confirms availability in the meeting |
| Planned work | 42.5 task hours plus about 12 hours of Scrum ceremonies |
| Submission deadline | Thursday 29 October 2026, 20:00 IST - GitHub repository link in the portal Submission area |

## 1.1 Proposed sprint goal

By Thursday 29 October 2026, the team will have a working GitHub repository with all 12 tables loaded and profiled, an entity-relationship diagram with validated joins, a first data-quality issue log, a KPI proposal of at least 10 KPIs and an agreed list of 15-20 analysis questions, all submitted through the CadetX portal.

This goal is a proposal for the team to discuss, adjust and agree on Day 1. It follows the programme brief, which asks teams to explore the dataset and propose their own KPIs and analysis questions before selecting further tasks.

## 1.2 Proposed team roles

| Member | Role | Focus this sprint |
| --- | --- | --- |
| Thomars | Scrum Master and Data Scientist | Ceremonies, tracking, repository set-up, coordinator contact, procurement and stock-ledger profiling, keys and ERD, review of the issue log, sprint notes and submission |
| Keren Oyem | Data Analyst | Environment and data load, master-table profiling, analysis questions, consolidated profiling notebook |
| David | Data Analyst | Sales and finance profiling, KPI proposal, data-quality issue log |

The Scrum Master role rotates weekly, as the programme requires. The proposed order is Thomars (Week 1), Keren Oyem (Week 2), David (Week 3), then repeating, so each member leads four sprints. The order is approved in Section 2.

# 2. Items for Discussion and Approval

These are the decisions the team needs to make in the planning meeting. Thomars records the outcome of each one in the last two columns during the meeting.

| No. | Item | Proposal | Decision (Agree / Change) | Notes / final decision |
| --- | --- | --- | --- | --- |
| 1 | Sprint goal | As in Section 1.1 |  |  |
| 2 | Roles | Thomars - Data Scientist; Keren Oyem and David - Data Analysts |  |  |
| 3 | Scrum Master rotation | Thomars (W1), Keren Oyem (W2), David (W3), then repeating |  |  |
| 4 | Task allocation and estimates | Sprint backlog in Section 6 (13 tasks, 42.5 hours) |  |  |
| 5 | Sprint rhythm | Sprints run Friday to Thursday; planning on Friday, review and retrospective on Wednesday, submission on Thursday by 20:00 IST |  |  |
| 6 | Daily stand-up time | 15 minutes at a fixed time, for example 21:00 IST (to be agreed) |  |  |
| 7 | Communication channel | One team channel for stand-ups and blockers (WhatsApp, Slack or Teams - to be agreed) |  |  |
| 8 | Weekly availability | About 20 hours per member per week; each member states their available days |  |  |
| 9 | GitHub workflow | Feature branches, pull requests reviewed by one other member, commit prefixes with member name |  |  |
| 10 | Tools | Python (Jupyter / VS Code), DuckDB, GitHub Projects; Power BI from Week 11 |  |  |
| 11 | Code freeze and submission | Code freeze 17:00 IST on Thursday; Scrum Master submits by 20:00 IST |  |  |
| 12 | Definition of Done | As in Section 10 |  |  |

Information each member brings to the meeting: GitHub username, available days and hours this week, preferred stand-up time, and any task they would like to swap.

# 3. Scrum Master Responsibilities This Week

| Responsibility | How it is delivered in Sprint 1 | When | Evidence on GitHub |
| --- | --- | --- | --- |
| Organise the weekly planning meeting | Send the invite with the agenda on Thursday 22 October; time-box the meeting to 60 minutes; take notes live. | Fri 23 Oct | sprint_plan.md |
| Define the sprint goal with the team | Present this draft (goal in Section 1.1), invite changes from Keren and David, and record approval from all three members (Sections 2 and 13). | Fri 23 Oct | Goal recorded in sprint_plan.md |
| Break the sprint into tasks and help allocate them | Split the work into 13 backlog items with owners, estimates and acceptance criteria (Section 6), balancing load across the team. | Thu 22 - Fri 23 Oct | Sprint backlog and GitHub issues |
| Coordinate and track progress | Run 15-minute daily stand-ups, update the project board and burndown daily, and remove blockers within 24 hours. | Daily | standups.md; burndown.md |
| Ensure every member contributes | Check commits, pull requests and stand-up attendance for each member daily; re-allocate work if anyone falls behind (Section 9). | Daily | Contribution tracker in sprint_notes.md |
| Upload the sprint notes to GitHub | Write sprint_notes.md, sprint_review.md and retro.md; update README; tag week-01; submit the link in the portal. | Thu 29 Oct | /sprints/week-01 folder; tag week-01 |

# 5. Sprint Planning Meeting

| Item | Detail |
| --- | --- |
| Date and time | Friday 23 October 2026, 60 minutes (online) |
| Facilitator | Thomars (Scrum Master) |
| Attendees | Thomars, Keren Oyem, David |
| Inputs | Programme brief, task catalogue, dataset files, 12-week roadmap, this draft plan |
| Outputs | Approved sprint plan v1.0: agreed goal, backlog with owners and estimates, working agreements, stand-up time, Scrum Master rotation |

| Time | Agenda item | Lead |
| --- | --- | --- |
| 0-5 min | Introductions and confirmation of roles (Thomars - SM and Data Scientist; Keren and David - Data Analysts) | Thomars |
| 5-15 min | Project context: business problem, 12-week roadmap, weekly submission and certification rules | Thomars |
| 15-25 min | Dataset walkthrough: 12 tables, about 605,000 rows, orders from January 2019 to December 2024 (Section 5.1) | Thomars |
| 25-35 min | Discuss and agree the sprint goal (Section 2, item 1) | All |
| 35-50 min | Walk through the backlog, confirm owners, estimates and availability (items 2, 4, 8) | All |
| 50-57 min | Working agreements, stand-up time, channel, rotation (items 3, 5-7, 9-12) | All |
| 57-60 min | Approval sign-off (Section 13) and next steps | Thomars |

## 5.1 Dataset facts to share at kick-off

- Master data: 6 branches in India, 30 heavy-machinery spare parts, 180 product-branch inventory rows, 8 suppliers in China and 500 customers.

- Transactions: 20,000 sales orders (130,402 lines), 24,000 purchase orders (155,495 lines), 18,033 invoices, 19,257 payments and 237,230 stock movements.

- Early quality signals to confirm during profiling: current stock is above maximum stock in all 180 product-branch rows; stock inflows are about 18 times outflows; some invoice payment statuses conflict with recorded payments; 2,370 purchase orders are cancelled and have no received date.

## 5.2 Proposed working agreements

- Daily stand-up at a fixed time agreed in the planning meeting (Section 2, item 6), 15 minutes, camera on where possible.

- Each member works on a feature branch and merges through a pull request reviewed by one other member.

- Commit messages start with the role and area, for example [DA-Keren] profiling: add products summary or [DS-Thomars] erd: add data model.

- Blockers are raised in the team channel immediately rather than waiting for the next stand-up.

- Code freeze at 17:00 IST on Thursday 29 October to leave time for submission.

# 6. Proposed Sprint Backlog

Total planned task effort is 42.5 hours. Owners and estimates are proposals; once approved, each item is created as a GitHub issue and assigned to its owner.

| ID | Task | Owner | Hours | Due | Acceptance criteria |
| --- | --- | --- | --- | --- | --- |
| S1-01 | Run the sprint planning meeting; publish sprint_plan.md with goal, backlog, owners and estimates | Thomars (SM) | 2.0 | Fri 23 | Plan pushed to /sprints/week-01; every member has at least two tasks |
| S1-02 | Confirm the team (Thomars, Keren Oyem, David) with the CadetX coordinator and request the missing Fields Documentation.docx | Thomars (SM) | 0.5 | Fri 23 | Message sent; reply logged in standups.md |
| S1-03 | Create the GitHub repository, folder structure, README skeleton, .gitignore, contributing rules and project board; invite both team members | Thomars (SM) | 2.0 | Fri 23 | All members can clone, branch and open pull requests |
| S1-04 | Set up the environment (requirements.txt, DuckDB) and load the 12 CSV files into /data/raw | Keren Oyem (DA) | 2.0 | Sat 24 | Row counts in DuckDB match the source files |
| S1-05 | Profile master tables: branches, products, inventory_master, suppliers, customers | Keren Oyem (DA) | 5.0 | Sun 25 | Shape, types, nulls, ranges, duplicates and categories documented per table |
| S1-06 | Profile sales and finance tables: sales_orders_header, sales_orders_lines, invoices, payments | David (DA) | 6.0 | Sun 25 | As S1-05, plus date coverage and header/line total checks |
| S1-07 | Profile procurement and stock tables: purchase_orders_header, purchase_orders_lines, stock_ledger | Thomars (DS) | 6.0 | Sun 25 | As S1-05, plus movement-type balance and running-balance checks |
| S1-08 | Validate primary and foreign keys; draw the ERD and write data_model.md | Thomars (DS) | 4.0 | Mon 26 | Every join tested; ERD image committed to /docs |
| S1-09 | Collect and consolidate 15-20 business analysis questions from all members | Keren Oyem (DA) | 2.0 | Mon 26 | Questions agreed by the team and stored in /docs |
| S1-10 | Draft the KPI proposal: at least 10 KPIs with formula, grain and source table | David (DA) | 4.0 | Tue 27 | kpi_proposal.md reviewed by one other member |
| S1-11 | Open the data-quality issue log v1 with severity, owner and proposed treatment (all members add findings) | David (DA) | 3.0 | Tue 27 | All profiling findings logged; reviewed by Thomars (DS) |
| S1-12 | Merge profiling work into 01_data_profiling.ipynb with a results summary | Keren Oyem (DA) | 3.0 | Wed 28 | Notebook runs top to bottom without errors |
| S1-13 | Facilitate the sprint review and retrospective; write sprint notes; update README; tag week-01; submit the link in the portal | Thomars (SM) | 3.0 | Thu 29 | Submission made by 20:00 IST; tag week-01 visible on GitHub |

## 6.1 Workload balance

| Member | Items | Task hours | Backlog items |
| --- | --- | --- | --- |
| Thomars (SM and DS) | 6 | 17.5 (SM 7.5, DS 10) | S1-01, S1-02, S1-03, S1-07, S1-08, S1-13 |
| Keren Oyem (DA) | 4 | 12 | S1-04, S1-05, S1-09, S1-12 |
| David (DA) | 3 | 13 | S1-06, S1-10, S1-11 |

Thomars carries 10 hours of Data Scientist work plus 7.5 hours of Scrum Master work. Keren and David each have 12-13 hours, leaving about 7-8 hours each for peer reviews, pull-request reviews and support.

# 7. Day-by-Day Plan

| Day | Date | Scrum Master activities | Team activities | Output |
| --- | --- | --- | --- | --- |
| Day 0 | Thu 22 Oct (prep) | Prepare: create the repository and project board, add the 13 backlog items as GitHub issues, invite Keren and David, send the meeting invite with the agenda, brief and dataset link. | Keren and David: accept the GitHub invitation and read the programme brief. | Repository and board ready |
| Day 1 | Fri 23 Oct | Sprint planning meeting (60 min). Agree goal, owners, estimates, stand-up time and working rules. Push sprint_plan.md. Send coordinator message (S1-02). | All: clone the repository and make a first commit (add own name and role to README). Keren: start S1-04. | sprint_plan.md; first commit from every member |
| Day 2 | Sat 24 Oct | Daily stand-up (15 min). Update the board and burndown. Follow up anyone without a commit. | Keren: finish data load (S1-04), start S1-05. David: start S1-06. Thomars (DS): start S1-07. | standups.md; data in /data/raw |
| Day 3 | Sun 25 Oct | Daily stand-up. Mid-sprint check: compare actual remaining hours with the plan and re-allocate work if anyone is blocked. | Finish profiling: Keren (S1-05), David (S1-06), Thomars (S1-07). Each pushes a profiling summary through a pull request. | Three profiling sections merged |
| Day 4 | Mon 26 Oct | Daily stand-up. Run a 30-minute peer-review session on the profiling outputs. | Thomars (DS): keys, ERD and data model (S1-08). Keren: analysis questions (S1-09). David: start KPI proposal (S1-10) and issue log (S1-11). | ERD; analysis questions |
| Day 5 | Tue 27 Oct | Daily stand-up. Check that each member has opened and reviewed at least one pull request. Remind the team of the Thursday deadline. | David: finish KPI proposal (S1-10) and issue log (S1-11). Thomars (DS): review the issue log. Keren: start merging the notebook (S1-12). | kpi_proposal.md; dq_issue_log.md v1 |
| Day 6 | Wed 28 Oct | Daily stand-up. Sprint review (45 min): each member demos their own work. Retrospective (30 min). Agree the Week 2 Scrum Master. | Keren: finish the notebook (S1-12). All: fix review comments. | sprint_review.md; retro.md |
| Day 7 | Thu 29 Oct | Definition of Done check at 17:00. Write sprint notes and contribution tracker, update README, tag week-01, submit the link by 20:00 IST (S1-13). Hand over to the next Scrum Master. | All: final pushes by 17:00 IST; confirm own contributions in sprint_notes.md. | Week 1 submission |

# 8. Progress Tracking

## 8.1 Daily stand-up format

- What did I complete since the last stand-up?

- What will I complete before the next stand-up?

- Is anything blocking me?

Thomars records each answer in standups.md, moves cards on the project board (To Do, In Progress, In Review, Done) and follows up on every blocker the same day.

## 8.2 Burndown

Remaining task hours are recorded at the end of each day. If the actual figure is more than 6 hours above the planned figure, Thomars re-allocates work or agrees a scope change with the team.

| Day | Planned remaining (h) | Actual remaining (h) | Planned completions |
| --- | --- | --- | --- |
| Start | 42.5 |  |  |
| Fri 23 Oct | 38.0 |  | S1-01, S1-02, S1-03 |
| Sat 24 Oct | 36.0 |  | S1-04 |
| Sun 25 Oct | 19.0 |  | S1-05, S1-06, S1-07 |
| Mon 26 Oct | 13.0 |  | S1-08, S1-09 |
| Tue 27 Oct | 6.0 |  | S1-10, S1-11 |
| Wed 28 Oct | 3.0 |  | S1-12 |
| Thu 29 Oct | 0.0 |  | S1-13; submitted |

# 9. Contribution Tracker

Thomars completes this table on Thursday 29 October and copies it into sprint_notes.md, because certificates and reference letters depend on visible individual contribution.

| Member | Tasks done | Commits | PRs opened | PRs reviewed | Stand-ups attended |
| --- | --- | --- | --- | --- | --- |
| Thomars (SM / DS) | / 6 |  |  |  | / 6 |
| Keren Oyem (DA) | / 4 |  |  |  | / 6 |
| David (DA) | / 3 |  |  |  | / 6 |

## 9.1 Minimum contribution rule

- Every member owns at least three backlog items and pushes commits on at least four of the seven days.

- Every member opens at least one pull request and reviews at least one pull request from another member.

- Every member presents their own output in the sprint review.

- If a member misses two stand-ups in a row, Thomars contacts them the same day and agrees a recovery plan.

# 10. Definition of Done

- The plan is approved by all three members (Section 13) and saved as sprint_plan.md v1.0.

- All 13 backlog items meet their acceptance criteria and are marked Done on the project board.

- All 12 tables are profiled and every join key is validated.

- The KPI proposal contains at least 10 KPIs with formula and source table.

- 01_data_profiling.ipynb runs from top to bottom and starts with a results summary.

- Sprint plan, stand-up log, burndown, sprint review, retrospective and sprint notes are in /sprints/week-01.

- README has a Week 1 entry, the tag week-01 exists, and the repository link is submitted by 20:00 IST on Thursday 29 October 2026.

# 11. Risks and Impediments

| Risk | Impact | Response |
| --- | --- | --- |
| A team member is unavailable for part of the week | High | Thomars re-allocates the item at the next stand-up and records the change in standups.md. |
| Thomars is overloaded holding both the Scrum Master and Data Scientist roles | Medium | Keep ceremonies time-boxed; ask Keren or David to take note-taking in the review and retrospective. |
| Fields Documentation.docx not received | Medium | Profile from the data itself and reconcile with the official guide when it arrives. |
| Large files (stock_ledger 14 MB, purchase_orders_lines 11 MB) slow down work | Medium | Load once into DuckDB and share the database file locally; keep raw CSVs unchanged. |
| Merge conflicts in the shared notebook | Medium | Each member works in a separate notebook section file; Keren merges on Wednesday 28 October. |
| Data-quality issues larger than expected | Low | Log them in the issue log; fixing them is planned for Sprint 2. |

# 12. GitHub Upload and Submission

## 12.1 Files in /sprints/week-01

| File | Updated | Content |
| --- | --- | --- |
| sprint_plan.md | Fri 23 Oct | Approved version of this plan: goal, backlog, owners, estimates, working agreements, decisions from Section 2 |
| standups.md | Daily | Done, next and blockers for each member each day |
| burndown.md | Daily | Planned and actual remaining hours |
| sprint_review.md | Wed 28 Oct | Demo notes, results summary, accepted and unfinished items |
| retro.md | Wed 28 Oct | Keep, improve, try; action owners |
| sprint_notes.md | Thu 29 Oct | Summary of the sprint, contribution tracker, links to outputs, next Scrum Master |

# 13. Approval

By signing below, each member confirms they have reviewed this plan, agree with the decisions recorded in Section 2, and accept the tasks assigned to them. Once all three members approve, the plan is saved as sprint_plan.md (v1.0) in /sprints/week-01.

| Member | Role | Approved (Yes / No) | Date | Comments |
| --- | --- | --- | --- | --- |
| Thomars | Scrum Master and Data Scientist |  |  |  |
| Keren Oyem | Data Analyst |  |  |  |
| David | Data Analyst |  |  |  |

# 14. Hand-over to Sprint 2

Sprint 2 runs from Friday 30 October to Thursday 5 November 2026 and covers data cleaning, validation and integrity checks (catalogue tasks A2, A5 and G4). The proposed Scrum Master is Keren Oyem (subject to approval in Section 2). The data-quality issue log from this sprint becomes the starting backlog for Sprint 2, and Thomars hands over the sprint files, the board and any open blockers on Thursday 29 October.

# Appendix A - Scrum Master Step-by-Step Checklist

These are the steps Thomars follows as Scrum Master from preparation on Thursday 22 October until the Week 1 outcome is submitted. Tick the last column as each step is completed. Thomars's own Data Scientist tasks (S1-07, S1-08 and the review in S1-11) run alongside these steps and are listed in the sprint backlog (Section 6).

## Before kick-off - Thu 22 Oct

| Step | Action | Done |
| --- | --- | --- |
| 1 | Create the team GitHub repository and add Keren Oyem and David as collaborators with write access. |  |
| 2 | Protect the main branch so every change goes through a pull request with one review. |  |
| 3 | Add the folder structure (data, notebooks, src, sql, docs, reports, dashboards, models, sprints/week-01, tests) and a README with the project summary and the team table. |  |
| 4 | Create a GitHub Project board with the columns To Do, In Progress, In Review and Done, and add backlog items S1-01 to S1-13 as issues with owner, estimate and due date. |  |
| 5 | Add empty templates for sprint_plan.md, standups.md and burndown.md in /sprints/week-01. |  |
| 6 | Send the planning meeting invite for Friday 23 October with the agenda (Section 5), the programme brief, the dataset link and this plan. |  |

## Day 1 - Fri 23 Oct

| Step | Action | Done |
| --- | --- | --- |
| 7 | Run the 60-minute planning meeting: confirm roles, explain the business problem, walk through the dataset, agree the sprint goal, confirm owners and estimates, and agree the stand-up time and working rules. |  |
| 8 | Write the decisions into sprint_plan.md and push it the same day. |  |
| 9 | Message the CadetX coordinator to register the team and request the Fields Documentation guide (S1-02). |  |
| 10 | Check that Keren and David have cloned the repository and pushed a first commit. |  |

## Every day - Sat 24 to Thu 29 Oct

| Step | Action | Done |
| --- | --- | --- |
| 11 | Run the 15-minute stand-up: done, next, blockers. Record each member's answers in standups.md. |  |
| 12 | Move cards on the board and record remaining hours in burndown.md. If the team is more than 6 hours behind the plan, re-allocate work or agree a scope change. |  |
| 13 | Clear blockers within 24 hours (access, data, tooling or unclear task). |  |
| 14 | Check each member's commits and pull requests so contribution stays visible and balanced. |  |

## Checkpoints during the sprint

| Step | Action | Done |
| --- | --- | --- |
| 15 | Sun 25 Oct - mid-sprint check: all three profiling tasks should be done; re-plan if not. |  |
| 16 | Mon 26 Oct - 30-minute peer review of profiling outputs; feed findings into the issue log. |  |
| 17 | Tue 27 Oct - confirm each member has opened and reviewed at least one pull request; remind everyone of the Thursday 17:00 IST code freeze. |  |

## Review and retrospective - Wed 28 Oct

| Step | Action | Done |
| --- | --- | --- |
| 18 | Run the sprint review (45 min): each member demos their own output; record accepted and unfinished items in sprint_review.md. |  |
| 19 | Run the retrospective (30 min): keep, improve, try, with an owner for each action; record in retro.md. |  |
| 20 | Agree the Week 2 Scrum Master (proposed rotation: Keren Oyem in Week 2, David in Week 3, Thomars in Week 4, and so on). |  |

## Delivery - Thu 29 Oct

| Step | Action | Done |
| --- | --- | --- |
| 21 | At 17:00 IST check every item against the Definition of Done (Section 10) and confirm all pull requests are merged. |  |
| 22 | Complete the contribution tracker and write sprint_notes.md. |  |
| 23 | Add the Week 1 entry to README.md with the goal, outputs and links. |  |
| 24 | Push with the commit message [SM] sprint-01: add sprint notes and review, then create the tag week-01. |  |
| 25 | Paste the repository link into the Submission area of the project in the CadetX portal before 20:00 IST. |  |
| 26 | Post the submission confirmation in the team channel and hand the sprint files to the Week 2 Scrum Master. |  |

# Appendix B - Sprint Notes Template

- Sprint and dates: Sprint 1, 23-29 October 2026

- Scrum Master: Thomars

- Team: Thomars (SM / DS), Keren Oyem (DA), David (DA)

- Sprint goal: as agreed in the planning meeting

- Completed items: IDs, owners and links

- Not completed items: IDs, reason and plan

- Key findings: three to five points from profiling

- Contribution tracker: table from Section 9

- Retrospective actions: what the team will change in Sprint 2

- Next Scrum Master: Keren Oyem (proposed)